## NANO_Milestone_Summary
Recruitment Milestones for MH132925 - The Role of Autonomic Regulation of Attention in the Emergence of ASD
Source status: no protocol-confirmed enrollment status/date mapping is present; diagnostic dates are not used. Missing values are N/A.
Tri Yearly Milestones | 2024 |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028
| Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1
Previous Target: Total Recruitment | 90 | 110 | 130 | 150 | 170 | 190 | 200 |  |  |  | 160
Current Target: Total Recruitment | 5 | 10 | 110 | 120 | 130 | 140 | 150 | 160 | 170 | 180 | 190 | 200
Actual: Total Recruitment | 63 | 108 | 128 | 151 | 172 | 219
Actual/Target Ratio: Total Recruitment
Status: Total Recruitment
Previous Target: Racial Minority Recruitment | 36 | 44 | 52 | 60 | 68 | 76 | 84 |  |  |  | 32
Current Target: Racial Minority Recruitment | 1 | 2 | [9 empty] | 40
Actual: Racial Minority Recruitment | 25 | 48 | 59 | 84 | 96 | 99
Actual/Target Ratio: Racial Minority Recruitment
Status: Racial Minority Recruitment
Previous Target: Hispanic Ethnicity Recruitment | 3 | 5 | 7 | 9 | 11 | 13 | 14 |  |  |  | 7
Current Target: Hispanic Ethnicity Recruitment |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 10
Actual: Hispanic Ethnicity Recruitment | 5 | 5 | 7 | 8 | 11 | 16
Actual/Target Ratio: Hispanic Ethnicity Recruitment
Status: Hispanic Ethnicity Recruitment
Source, access, and mapping evidence
Project key | NANO
Observed REDCap project ID | 4218
Observed REDCap project title | NANO Study Surveys
Report cutoff | 2026-09-12
Enrollment-status mapping | N/A - no protocol-confirmed field/rule in repository evidence
Enrollment-date mapping | N/A - no protocol-confirmed enrollment/consent date
Target provenance | Values transcribed unchanged from the user-supplied reference table and the existing repository configuration; protocol verification is not present in the repository.
Actual provenance | Published cumulative values transcribed unchanged from the user-supplied reference table; no enrollment-date recomputation.
Required API reads | project_info, metadata, instruments, events, event_mappings, minimal_records
Participant records visible to token | 221
Unresolved inclusion | 206
Definitely excluded by source flags | 15