## NANO
Year | 2024 |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028
Milestone | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1
Previous Target: Total Recruitment | 90 | 110 | 130 | 150 | 170 | 190 | 200 |  |  |  | 160
Current Target: Total Recruitment | 5 | 10 | 110 | 120 | 130 | 140 | 150 | 160 | 170 | 180 | 190 | 200
Actual: Total Recruitment | 63 | 108 | 128 | 151 | 172 | 219
Previous Target: Racial Minority Recruitment | 36 | 44 | 52 | 60 | 68 | 76 | 84 |  |  |  | 32
Current Target: Racial Minority Recruitment | 1 | 2 | [9 empty] | 40
Actual: Racial Minority Recruitment | 25 | 48 | 59 | 84 | 96 | 99
Previous Target: Hispanic Ethnicity Recruitment | 3 | 5 | 7 | 9 | 11 | 13 | 14 |  |  |  | 7
Current Target: Hispanic Ethnicity Recruitment |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 10
Actual: Hispanic Ethnicity Recruitment | 5 | 5 | 7 | 8 | 11 | 16

## NICO
Year | 2024 |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028
Milestone | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1
Previous Target: Total Recruitment
Current Target: Total Recruitment
Actual: Total Recruitment | [5 empty] | 82
Previous Target: Racial Minority Recruitment
Current Target: Racial Minority Recruitment
Actual: Racial Minority Recruitment | [5 empty] | 53
Previous Target: Hispanic Ethnicity Recruitment
Current Target: Hispanic Ethnicity Recruitment
Actual: Hispanic Ethnicity Recruitment | [5 empty] | 7

## provenance
Project | Metric | Current target series | Source | Status
NANO | Total Recruitment | [5, 10, 110, 120, 130, 140, 150, 160, 170, 180, 190, 200] | prior reporting config — not reconciled to NIH plan | provisional (UNVERIFIED)
NANO | Racial Minority Recruitment | [1, 2, None, None, None, None, None, None, None, None, None, 40] | prior reporting config — not reconciled to NIH plan | provisional (UNVERIFIED)
NANO | Hispanic Ethnicity Recruitment | [None, None, 1, None, 1, None, 1, None, 1, None, 1, 10] | prior reporting config — not reconciled to NIH plan | provisional (UNVERIFIED)
NICO | Total Recruitment | — | NOT SUPPLIED | MISSING
NICO | Racial Minority Recruitment | — | NOT SUPPLIED | MISSING
NICO | Hispanic Ethnicity Recruitment | — | NOT SUPPLIED | MISSING

## funnel
Project | Raw exported rows | Unique participants | Included (clean) | Flagged-review (still counted) | Excluded (removed) | Counted in cumulative
NANO | 254 | 219 | 197 | 22 | 0 | 219
NICO | 111 | 82 | 78 | 4 | 0 | 82