## NANO
NANO Study Recruitment Milestones
Report date 2026-07-23 Counting policy: all unique records counted; ineligible/unenrolled and quality issues flagged No date candidate is treated as verified protocol enrollment; live counts are not backfilled into a milestone.
Metric | Aug 1 2024 | Dec 1 2024 | Apr 1 2025 | Aug 1 2025 | Dec 1 2025 | Apr 1 2026 | Aug 1 2026 | Dec 1 2026 | Apr 1 2027 | Aug 1 2027 | Dec 1 2027 | Apr 1 2028 | Aug 1 2028 | Dec 1 2028 | Live as of 2026-07-23
Previous Target: Total Recruitment | 90 | 110 | 130 | 150 | 170 | 190 | 200 |  |  |  | 160 |  |  |  | 200
Current Target: Total Recruitment | 5 | 10 | 110 | 120 | 130 | 140 | 150 | 160 | 170 | 180 | 190 | 200 |  |  | 150
Published Historical Actual / Live-as-of Count: Total Recruitment | 63 | 108 | 128 | 151 | 172 | 219 | [8 empty] | 219
Actual / Current Target: Total Recruitment
Status: Total Recruitment | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified
Previous Target: Racial Minority Recruitment | 36 | 44 | 52 | 60 | 68 | 76 | 84 |  |  |  | 32 |  |  |  | 84
Current Target: Racial Minority Recruitment | 1 | 2 | [9 empty] | 40
Published Historical Actual / Live-as-of Count: Racial Minority Recruitment | 25 | 48 | 59 | 84 | 90–99 | 90–99 | [8 empty] | 99
Actual / Current Target: Racial Minority Recruitment
Status: Racial Minority Recruitment | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified
Previous Target: Hispanic Ethnicity Recruitment | 3 | 5 | 7 | 9 | 11 | 13 | 14 |  |  |  | 7 |  |  |  | 14
Current Target: Hispanic Ethnicity Recruitment |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 10 |  |  | 1
Published Historical Actual / Live-as-of Count: Hispanic Ethnicity Recruitment | <10 | <10 | <10 | <10 | 10–19 | 10–19 | [8 empty] | 16
Actual / Current Target: Hispanic Ethnicity Recruitment
Status: Hispanic Ethnicity Recruitment | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified | N/A — target unverified

## Run Summary
Project | REDCap PID | Project title | Report date | Generated UTC | Counting policy | Public count policy | Live total | Live racial minority | Observed live Hispanic/Latino | Ethnicity missing/unknown | Demographic classification state | Demographic classification note
NANO | 4218 | NANO Study Surveys | 2026-07-23 | 2026-07-23 20:28 | all unique records counted; ineligible/unenrolled and quality issues flagged | Participant-derived cells 1–9 are <10; diagnostics and temporally complementary cumulative cells are banded | 219 | 99 | 16 | 10–19 | configured; pending study-owner policy confirmation | Codes match the exported data dictionary; minority/Hispanic reporting rules still require study-owner approval

## Data Quality
Project | Metric | Value
NANO | Flagged for review | 30–39
NANO | Would be excluded under strict policy | 10–19
NANO | Race missing | <10
NANO | Race unknown/other | <10
NANO | Ethnicity missing/unknown | 10–19
NANO | Dual-enrolled in NANO | 0

## Date Candidates
Project | Field | Description | Participants with valid date | Participants with invalid date | Participants with multiple dates | Interpretation
NANO | visit_date | Visit date | 210–219 | 0 | 190–199 | Diagnostic candidate; not used as enrollment date
NANO | bsrc_doe | Data-sharing consent date | 200–209 | 0 | 0 | Diagnostic candidate; not used as enrollment date
NANO | papf_parent_date | Optional media/advertising form date | 210–219 | 0 | 0 | Diagnostic candidate; not used as enrollment date
NANO | fif_doe | Family information evaluation date | 200–209 | 0 | 40–49 | Diagnostic candidate; not used as enrollment date

## Provenance
Project | Metric | Target state | Target source | Historical source | Enrollment date status | Demographic classification state | Demographic classification note | Ratio definition
NANO | Total Recruitment | provisional / unverified | Prior reporting configuration; not reconciled to the NIH-approved plan | Published cumulative history | No verified field; candidates are diagnostic only | configured; pending study-owner policy confirmation | Codes match the exported data dictionary; minority/Hispanic reporting rules still require study-owner approval | Calculated only after target verification; otherwise suppressed
NANO | Racial Minority Recruitment | provisional / unverified | Prior reporting configuration; not reconciled to the NIH-approved plan | Published cumulative history | No verified field; candidates are diagnostic only | configured; pending study-owner policy confirmation | Codes match the exported data dictionary; minority/Hispanic reporting rules still require study-owner approval | Calculated only after target verification; otherwise suppressed
NANO | Hispanic Ethnicity Recruitment | provisional / unverified | Prior reporting configuration; not reconciled to the NIH-approved plan | Published cumulative history | No verified field; candidates are diagnostic only | configured; pending study-owner policy confirmation | Codes match the exported data dictionary; minority/Hispanic reporting rules still require study-owner approval | Calculated only after target verification; otherwise suppressed

## QA Checks
Project | Check | Passed | Detail
NANO | Configured REDCap project identity | TRUE | PID 4218
NANO | One audit row per participant | TRUE | Audit keys are unique
NANO | Cumulative total reconciles to audit | TRUE | Matches calculated live count
NANO | Demographic categories do not exceed total | TRUE | Both category counts are within the live total
NANO | No unverified enrollment date inferred | TRUE | All date fields are diagnostic candidates only