## NANO
Year | 2024 |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028
Milestone | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1
Previous Target: Total Recruitment | 90 | 110 | 130 | 150 | 170 | 190 | 200 |  |  |  | 160
Current Target: Total Recruitment | 5 | 10 | 110 | 120 | 130 | 140 | 150 | 160 | 170 | 180 | 190 | 200
Actual: Total Recruitment | 63 | 108 | 128 | 151 | 172 | 219
Actual/Target Ratio: Total Recruitment | 1260% | 1080% | 116% | 126% | 132% | 156% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Status: Total Recruitment | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | 📋 | [5 empty] | N/A | N/A
Previous Target: Racial Minority Recruitment | 36 | 44 | 52 | 60 | 68 | 76 | 84 |  |  |  | 32
Current Target: Racial Minority Recruitment | 1 | 2 | [9 empty] | 40
Actual: Racial Minority Recruitment | 25 | 48 | 59 | 84 | 96 | 99
Actual/Target Ratio: Racial Minority Recruitment | 2500% | 2400% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Status: Racial Minority Recruitment | ✅ | ✅ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A
Previous Target: Hispanic Ethnicity Recruitment | 3 | 5 | 7 | 9 | 11 | 13 | 14 |  |  |  | 7
Current Target: Hispanic Ethnicity Recruitment |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 10
Actual: Hispanic Ethnicity Recruitment | 5 | 5 | 7 | 8 | 11 | 16
Actual/Target Ratio: Hispanic Ethnicity Recruitment | N/A | N/A | 700% | N/A | 1100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Status: Hispanic Ethnicity Recruitment | N/A | N/A | ✅ | N/A | ✅ | N/A | 📋 | N/A |  | N/A |  |  | N/A | N/A

## NICO
Year | 2024 |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028
Milestone | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1 | Apr 1 | Aug 1 | Dec 1
Previous Target: Total Recruitment
Current Target: Total Recruitment
Actual: Total Recruitment
Actual/Target Ratio: Total Recruitment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Status: Total Recruitment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Previous Target: Racial Minority Recruitment
Current Target: Racial Minority Recruitment
Actual: Racial Minority Recruitment
Actual/Target Ratio: Racial Minority Recruitment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Status: Racial Minority Recruitment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Previous Target: Hispanic Ethnicity Recruitment
Current Target: Hispanic Ethnicity Recruitment
Actual: Hispanic Ethnicity Recruitment
Actual/Target Ratio: Hispanic Ethnicity Recruitment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Status: Hispanic Ethnicity Recruitment | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A